## Phases & Budget
Phase | Hours | USD ($25/hr) | INR (₹88.5/USD) | Duration
A. Core Stability & Infra | 90 | 2250 | 199125 | 3 weeks
B. Data Sources & Verification | 180 | 4500 | 398250 | 4 weeks
C. Financial Analytics (Lynch + Multibagger) | 240 | 6000 | 531000 | 5 weeks
D. Dashboards & Reporting Suite | 140 | 3500 | 309750 | 3 weeks
E. Ops, Security, Compliance | 120 | 3000 | 265500 | 3 weeks
F. Testing & Contingency Buffer | 60 | 1500 | 132750 | 2 weeks

## Infra Budget
Tier | Infra Components | INR (Min) | INR (Max) | USD (Min) | USD (Max)
Free / Minimal | GitHub Actions, SQLite, Slack Free | 0 | 1800 | 0 | 20
Mid (Pro) | Supabase/Postgres, NewsAPI Pro, Monitoring | 8800 | 22000 | 100 | 250
Enterprise | Bloomberg/Factiva, Cloud Ops SLA | 88000 | 177000 | 1000 | 2000

## 90-Day Plan
Month | Key Goals
Nov 2025 | Finalize Slack & Telegram alert loop, Verify influencer CSV, Add NSE/BSE fetchers
Dec 2025 | Implement Peter Lynch & Growth Quality calculators, DB migration to Postgres
Jan 2026 | Complete multibagger scoring engine, Streamlit dashboard prototype, Email digest
Feb 2026 | Security hardening, logging & retries, telemetry alerts
Mar 2026 | Optional AI/NLP and relationship graph layer

## Risks
Risk | Mitigation
API changes / rate limits | Caching + throttling logic
Feed license restrictions | Legal review & ToS compliance
Computation cost spikes | Nightly jobs for heavy tasks
False positives in analytics | Cross-validation & manual review
Data loss | Automated DB snapshots

## In-House Efforts
All architectural design, coding, debugging, pipeline integration, and testing have been performed in-house by Business Falauda with GPT-5 as engineering assistant. No external billing incurred; the above monetary values represent equivalent engineering effort value.